GREEN AFRICA HUB LTD

Company No. 17107299  |  Incorporated 21 March 2026

www.greenafricahub.org.uk  |  gracetuase@gmail.com  |  +44 (0) 7776 643169

Bristol, England & Wales

Business Plan — General Version

Version 2.0 — March 2026

Updated following Future Leap advisor review

Business Confidential

"Sustainability is everyone's business — and should be the business of everyone." Green Africa Hub exists to ensure that Black communities are not just part of the green transition but leading it — protecting our heritage, powering our future, and making this planet a better place for our children, our communities, and for all.

Table of Contents

1.  Executive Summary

2.  The Founder — Grace's Story  [NEW]

3.  The Problem

4.  The Solution — Smart Kitchen Hub

5.  The Pilot Plan  [NEW]

6.  Revenue Model

7.  Break-Even Analysis  [NEW]

8.  Market Opportunity

9.  Operations & Timeline

10.  Funding Strategy

11.  SDG Alignment

12.  Risk Register

13.  Conclusion

# 1. Executive Summary

Green Africa Hub Ltd is a newly incorporated UK social enterprise (Company No. 17107299, incorporated 21 March 2026) addressing a critical and underserved market gap: African and Caribbean communities in the UK are disproportionately affected by fuel poverty and have been systematically excluded from the green technology transition.

The business is led by Grace Omotuase — a Chartered Manager, Data Scientist, and professional cook with 14 years of financial leadership including 12 years at the Central Bank of Nigeria. Through 18 months of pre-incorporation research, Grace has developed a proprietary Smart-Prep Methodology™ that adapts traditional African and Caribbean recipes for energy-efficient induction cooking, alongside an AI carbon tracking dashboard built in Python, Scikit-learn, and Power BI.

Green Africa Hub operates a hybrid model with five revenue streams:

- In-person Smart Kitchen Hub sessions (from £10/session)

- Digital learning subscriptions (from £10/month)

- Kitchen memberships for micro-caterers (from £50/month)

- Equipment referral commissions (10–15% per sale)

- B2B sustainability consulting and events (from £500/engagement)

## At a Glance

| Mission | To make African and Caribbean cooking affordable, green, and future-proof. |
| --- | --- |
| Innovation | UK's first AI-powered carbon tracking Smart Kitchen Hub for African/Caribbean food culture. |
| Pilot | 3 community sessions planned for April–June 2026 (proof of demand) |
| Revenue | Year 1 £28,200 → Year 2 £87,500 → Year 3 £152,000 |
| Break-even | Month 7–8 (blended model); 11 sessions/month (sessions only) |
| Jobs | 2 (Year 1) → 5 (Year 2) → 10+ (Year 3) |
| Funding | Bootstrapped. Grant pipeline: £125,000+ targeted (Innovate UK, UKSPF, WECA, National Lottery) |
| Partner | Future Leap (WECA-funded) — confirmed sustainability and facilities partner |

# 2. The Founder — Grace's Story

[NEW — Added following advisor feedback that funders back people as much as ideas]

Grace Omotuase is not a typical startup founder. She came to this business through a lifetime of experience — financial leadership at scale, technical expertise in data science and AI, professional cookery training, and a deep personal connection to African and Caribbean food culture.

Born in Nigeria, Grace spent 12 years at the Central Bank of Nigeria managing teams of 30+ staff and overseeing financial programmes exceeding £300 million. She later pursued advanced qualifications in the UK — an MSc in Financial Technology at the University of Bradford, a Data Science Certificate at the University of Texas at Austin, a Professional Cookery qualification at Bradford College, Chartered Manager status through the Chartered Management Institute, CIMA Management Level, IBM AI Fundamentals, and CMI Level 5 Leadership & Management.

But her path to Green Africa Hub began not in a boardroom or a lecture hall — it began in her kitchen.

"My lightbulb moment came from a simple observation: the conflict between tradition and the cost of living. I saw talented home cooks and micro-caterers — women I knew, families I respected — struggling with massive gas bills and the rising cost of imported staples. I watched the green technology conversation happen entirely around and above them, as if their kitchens didn't matter. I realised that if we didn't find a way to make our cultural cooking green, it would eventually become too expensive to survive. Our children would grow up without the flavours that connect them to home. And our community would be left behind — again — in a transition that affects all of us. Green Africa Hub is my answer to that. It is built from lived experience, professional expertise, and a conviction that our heritage and our future are not in conflict. They are the same journey." — Grace Omotuase, Founder & CEO

Grace spent 18 months before incorporation developing and testing the Smart-Prep Methodology™ — personally adapting 11 traditional recipes for energy-efficient induction cooking, building and validating the carbon accounting framework against DEFRA 2025 emissions factors, and developing the AI carbon tracking dashboard prototype. She completed the WECA Sustainability in Business Bootcamp at Future Leap in March 2026, which provided institutional validation, community connections, and direct advisor feedback that has been incorporated into Version 2.0 of this business plan.

# 3. The Problem

African and Caribbean households and micro-food businesses in the UK face four interconnected challenges:

## 3.1 Rising Energy Costs

Traditional African and Caribbean cooking relies on gas for extended high-heat methods — long-simmering stews, deep frying, steaming over high heat. With UK gas prices rising over 40% since 2021, small caterers and households face unmanageable costs. Average energy bills for African and Caribbean households run £2,400–£3,200 annually, approximately 40% above the national average. Fuel poverty rates in Black African and Black Caribbean communities run at 25–30%, compared to the 13% national average (ONS, 2021 Census data).

## 3.2 High Carbon Footprint

Gas cooking produces significant Scope 1 emissions directly in the home. Imported ingredients — plantains, yams, scotch bonnets, palm oil — create Scope 3 supply chain emissions. Neither is currently tracked or managed by community caterers. The vast majority of African and Caribbean micro-food businesses have no carbon footprint data at all, making them unable to meet emerging ESG requirements or access green economy funding.

## 3.3 Exclusion from Green Technology

Based on community engagement during the WECA Sustainability in Business Bootcamp (March 2026) and direct conversations with Bristol's African and Caribbean food community, Green Africa Hub's founder observed that the overwhelming majority of small African and Caribbean community caterers have not accessed green kitchen technology. The barriers are consistent: high upfront costs of quality induction equipment (£600–£1,500), no community-specific guidance or demonstration, and a widespread perception — understandable given the lack of evidence to the contrary — that induction technology cannot replicate the results of traditional gas cooking.

Note: This observation is based on Grace Omotuase's direct community engagement and the WECA Bootcamp research process. Formal market research will be conducted during the pilot phase (April–June 2026) to generate quantified data.

## 3.4 The Cultural Dimension

Many African and Caribbean cooks believe — often correctly, based on their experience of poorly adapted equipment — that induction cooking cannot replicate traditional methods. This perception, combined with high costs and a lack of trusted guidance from within the community, perpetuates gas dependency despite its economic and environmental costs. Green Africa Hub addresses this not through generic sustainability messaging, but through culturally credible demonstration: Grace cooks the food herself, in the community, with the technology.

# 4. The Solution — Smart Kitchen Hub

## 4.1 Smart-Prep Methodology™

Green Africa Hub's core proprietary asset is the Smart-Prep Methodology™ — a systematic process for adapting traditional African and Caribbean recipes to energy-efficient induction cooking. Each adapted recipe preserves cultural authenticity while reducing energy consumption and carbon emissions.

Current status: 11 fully tested and validated recipes completed. 40+ in development pipeline. Trademark application in preparation (Q2 2026, Classes 41, 42, 43).

## 4.2 AI Carbon Tracking Dashboard

The UK's first AI-powered carbon tracking tool designed specifically for African and Caribbean cooking. Built by Grace using Python, Scikit-learn, and Power BI — the tool maps each recipe's ingredients and cooking method to real emissions data using DEFRA 2025 factors and recommends culturally appropriate lower-carbon alternatives. Prototype functional. Pilot with 50 households planned for Year 1.

## 4.3 Smart Kitchen Hub — Bristol

A community-facing hub in Bristol combining:

- Shared electric induction cooking facilities

- In-person Smart-Prep cooking sessions

- Live carbon tracking and education

- Food safety and allergen training

- Digital subscription platform access

Partnership with Future Leap (WECA-funded) confirmed for facilities access during Year 1.

## 4.4 Hub & Spoke Scalability

Bristol Hub provides centralised R&D, content creation, and quality assurance. Licensed community Spokes deliver local training in Birmingham (Year 2) and Manchester (Year 2–3), scaling to 10+ UK cities by Year 5. Digital platform provides national reach from Day 1.

# 5. The Pilot Plan — April–June 2026

[NEW — Added following Future Leap advisor recommendation]

Before approaching funders for larger capital, Green Africa Hub will run a structured 3-session community pilot to generate real evidence of demand, willingness to pay, and programme impact.

## Pilot Structure

- 3 sessions: April, May, June 2026

- Venue: Community kitchen in Bristol (approached via pilot proposal — zero venue cost)

- Participants: 8–15 per session

- Session themes: Smart-Prep Basics / African Flavours, Green Futures / Carbon Tracking in Your Kitchen

- Cost to participants: Free (pilot phase)

- Equipment: Grace's own portable induction equipment

## What the Pilot Will Measure

| Metric | Purpose |
| --- | --- |
| Attendance and return rate | Measures demand and engagement |
| Participant feedback scores | Validates programme quality |
| Estimated CO₂ saved per session vs gas equivalent | Quantifies environmental impact |
| Average energy cost saving per household per meal | Demonstrates economic value |
| Willingness to pay for ongoing sessions | Validates pricing model |
| Interest in digital subscription | Tests digital revenue stream potential |

## Why This Matters

The pilot transforms the funding pitch from a promising idea into an evidenced proposition. Three sessions with 10 participants each generates 30 real data points — attendance figures, feedback scores, energy savings, and expressed demand. This data will be presented to grant funders from July 2026 onwards and is expected to significantly strengthen applications to Innovate UK, UKSPF, and the WECA Green Economy Fund.

# 6. Revenue Model

Five diversified revenue streams reduce dependency on any single source:

| Revenue Stream | Pricing | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- | --- |
| In-person sessions | £10–£50/session | £8,400 | £28,800 | £54,000 |
| Digital subscriptions | £10–£20/month | £7,200 | £28,800 | £57,600 |
| Kitchen memberships | £50–£100/month | £6,000 | £18,000 | £24,000 |
| Equipment commissions | 10–15% per sale | £2,600 | £6,500 | £10,400 |
| B2B consulting & events | £500–£2,500 | £4,000 | £5,400 | £6,000 |
| TOTAL |  | £28,200 | £87,500 | £152,000 |

# 7. Break-Even Analysis

[NEW — Added following Future Leap advisor recommendation]

## Break-Even Summary

| Fixed monthly costs | £1,080 |
| --- | --- |
| Variable cost per session | £60 |
| Average session revenue (8 × £20) | £160 |
| Contribution margin per session | £100 |
| Sessions-only break-even | 11 sessions/month |
| Blended break-even | Month 7–8 |
| Year 1 total revenue | £28,200 |
| Year 1 total costs | £20,160 |
| Year 1 net surplus | £8,040 |

## Fixed Monthly Costs: £1,080

- Hub space hire: £800

- Insurance: £80

- Website/tools: £50

- Marketing: £100

- Admin: £50

## Variable Cost per Session: £60

- Ingredients: £40

- Materials: £5

- Equipment: £10

- Energy: £5

## Sessions-Only Break-Even: 11 Sessions per Month

Average session revenue: £160 (8 participants × £20 average) minus variable cost of £60 = contribution margin of £100 per session. Fixed costs of £1,080 ÷ £100 contribution margin = 10.8, rounded up to 11 sessions per month.

## Blended Break-Even: Month 7–8

By Month 6, combining all five revenue streams:

- Sessions: ~£700

- Subscriptions: ~£450

- Memberships: ~£375

- Commissions: ~£130

- Consulting: ~£333

Total Month 6 revenue: ~£1,988 vs total costs ~£1,500 = £488 surplus.

Cumulative break-even (costs recovered): Month 7–8.

## Year 1 Summary

Total revenue: £28,200  |  Total costs: £20,160  |  Net surplus: £8,040

The full interactive financial model with month-by-month projections is available as a separate Excel workbook (GreenAfricaHub_BreakEven_Model_v2.xlsx).

# 8. Market Opportunity

Primary market: ~1.5 million UK African and Caribbean diaspora (ONS Census 2021). Concentrated in Bristol, Birmingham, Manchester, London. Fuel poverty rate 25–30% vs 13% national average.

Bristol target community: 15,000–20,000 Black African and Black Caribbean residents. Established food culture with regular cultural events, markets, and community catering.

UK micro-caterers: An estimated 5,000–8,000 informal African and Caribbean food businesses operate across the UK, most with no access to green technology or sustainability education.

UK sustainable food market: £14 billion+ (2024), growing driven by consumer demand and regulatory pressure.

## Competitive Position

No direct competitors. Green Africa Hub is the first organisation combining cultural food expertise, AI carbon tracking technology, institutional sustainability partnerships, and a completed recipe library — all specifically for African and Caribbean communities in the UK.

# 9. Operations & Timeline

## Year 1 (2026) — Pilot & Launch

Q1–Q2: 3-session community pilot (April–June). Data collection and analysis.

Q2: Grant applications submitted (Innovate UK, UKSPF, WECA Green Economy Fund, National Lottery).

Q3: Bristol Smart Kitchen Hub launched with Future Leap. Digital subscription platform live.

Q4: AI Carbon Tracker pilot with 50 households. Kitchen membership programme launched.

## Year 2 (2027) — Growth

Birmingham spoke launched. Digital subscriptions scaled nationally. 5 staff members.

## Year 3 (2028) — Scale

Manchester spoke. SaaS carbon tracker licensing begins. 10+ staff. £152,000 revenue.

# 10. Funding Strategy

Bootstrapped to date. No external funding raised.

## Grant Pipeline — Targeting £125,000+

| Grant Programme | Target Amount | Focus Area |
| --- | --- | --- |
| Innovate UK | £20,000 | AI innovation — carbon tracker |
| UKSPF (UK Shared Prosperity Fund) | £10,000 | Community sustainability |
| WECA Green Economy Fund | £8,000 | Bristol green SME |
| National Lottery Community Fund | £7,500 | Social impact |

Applications staggered Q2–Q3 2026, following completion of the pilot programme which will provide demand evidence to strengthen all applications.

# 11. SDG Alignment

Green Africa Hub's work aligns with eight United Nations Sustainable Development Goals:

| SDG | Alignment |
| --- | --- |
| SDG 1 | No Poverty — Reducing fuel poverty in African/Caribbean households |
| SDG 2 | Zero Hunger — Sustainable food systems and cultural food security |
| SDG 7 | Affordable Clean Energy — Transition from gas to induction cooking |
| SDG 8 | Decent Work — Creating skilled green economy jobs |
| SDG 10 | Reduced Inequalities — Ensuring Black communities lead — not follow — the green transition |
| SDG 12 | Responsible Consumption — Carbon tracking and sustainable sourcing |
| SDG 13 | Climate Action — Measurable community-level carbon reduction |
| SDG 17 | Partnerships — Future Leap, WECA, NHS, and local authority collaboration |

# 12. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Low pilot attendance | Medium | High | Target existing Future Leap and community networks; sessions free in pilot phase |
| Grant applications unsuccessful | Medium | Medium | Diversified 5-stream revenue; bootstrapped model reduces grant dependency |
| Kitchen space costs overrun | Low | High | Future Leap partnership reduces Year 1 space costs; pilot uses borrowed venues |
| Digital platform delayed | Low | Medium | MVP subscription launched on existing platform before custom build |
| Founder capacity | Medium | High | Phased hiring: admin support in Month 6, facilitator in Month 9 |

# 13. Conclusion

Green Africa Hub is a well-timed, evidence-based social enterprise with a clear market gap, a technically credible founder, and a lean, scalable model. The next immediate step — running three community pilot sessions between April and June 2026 — will generate the real-world demand evidence that transforms this business plan from a strong proposal into a fundable, proven proposition.

The concept is right. The timing is right. The founder is right. The pilot is the next right step.

For enquiries:

Grace Omotuase  |  gracetuase@gmail.com  |  07776 643169

www.greenafricahub.org.uk